## Options for 2019 Strategic Plan
|  | Option 1 | Option 2 | Option 3
Summary | Prof | -Primarily Staff -Low level of input collected, public participation, and professional assistance -Hire consulting services for some process design, information synthesis, advice on survey and advice on performance measures | -Staff/Consultant Services -Medium level of input collected, public participation, and professional assistance -Hire consulting services for process design, meeting design and facilitation of multi-session planning process, basic situational assessment, and performance measurement consultation | -Primarily Consultant Services -High level of input collected, public participation, and professional assistance -Hire consultant for process design and planning and overall project management, meeting design and facilitation of multi-session planning process, comprehensive situation assessment, performance measurement consultation, and implementation planning
Basic Planning Elements
Collect Information |  | Update information on existing resources (See Appendix 1: Environment and Natural Resources Plans, Documents and Reports) | Basic gathering and synthesis of information on existing resources such as natural resource programs, documents, plans, and reports | Comprehensive gathering and synthesis of information on existing resources such as natural resource programs, documents, plans, and reports
Identify Issues and Interests |  | Member Interest Survey Stakeholder Interest Survey Regional Site Visits | Member Interest Survey Stakeholder Interest Survey Regional Site Visits Online Citizen Input Forum Call for abstracts and ideas | Member Interest Survey Stakeholder Interest Survey Regional Site Visits Online Citizen Input Forum Call for abstracts and ideas Regional Forums Statewide survey
Review Information and Public Input |  | Review and Evaluate Existing Information Collected and Identified Presentations or information requests | Review and Evaluate Existing Information Collected and Identified Presentations or information requests Interviews and focus groups | Review and Evaluate Existing Information Collected and Identified Presentations or information requests Interviews and focus groups Host State Conference
Draft Strategic Plan |  | Regular LCCMR meeting to update current strategic plan | One day strategic plan workshop for members to draft a new six year strategic plan Draft operations/implementation plan | Two day strategic plan workshop for members to draft a new six year strategic plan Draft operations/implementation plan
Finalize Plan |  | Revise and adopt | Public review and comment, revise and adopt | Public review and comment, revise and adopt
Approximate Cost Range |  | $50,000-$75,000 | $75,000-$125,000 | $125,000 and Up
Commission voted on 11/13/2018 to pursue option #2.